## Sheet1
Activities |  |  | week 1 | week 2 | week 3 | week4 | week 5 | week 6 | week 7 | week 8 | week 9 | week 10 | week 11 | week 12
|  |  | 15th Oct | 22nd Oct | 29th oct | 5th Nov | 12th Nov | 19th Nov | 26th Nov | 3rd dec | 10th Dec | 17th Dec | 24th Dec | 26th Dec
Branding RO Project
Violence
1982 coup | Cyberspace | Cheetah | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral
Will avenge / is revenge full | Telephone | Cheetah | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting
Prosecution & persecution of past leaders | Telephone | Giraffe | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending
| Nationaly | Cheetah | week 1: xxx; week 2: circulation of one million leaflets
| Nationaly | Stork | week 1: xxx; week 2: Publishing of Mundia story on Citizen 1st page
Documentaries on Coups & Violence in Africa | KBC | Cheetah | week 1: Rwanda; week 2: Sierra Leone; week 3: Ivory Coast; week4: DRC
All bodyguards ex 1982 ex con’s led by Lumumba, Head of security, a vicious killer | KBC | Cheetah | week 1: xxx; week 2: "Events that Shook kenya" weekly Show
Sold us to Americans | Nationaly | Cheetah | week 1: Cartoons; week 2: Cartoons
Luo violence will take over | Nationaly | KBC (Cheetah 2 action) | Focus on Presidential Candidates | Kalonzo | Dr Ojiambo | Nyaga | Mudavadi | Ruto | RO | Tuju | Kirwa | Uhuru | Kombo | Candidate
All violence in E.A led by O ie Obote, Okello, Odinga, ojamong | Nationaly | KBC (Cheetah 2 action) | week 1: Promote weekend movie of Hotel Rwanda; week 2: Show the "Hotel Rwanda Film"
| Nationaly | Giraffe | week 1: Make people in our zones fear RO leadership; week 2: Run TV adverts around "Hotel Rwanda" E7
| NTV or KTN | Dolphin | week 1: xxx; week 2: TV discussion show on "Violence"
| KBC | KBC (Cheetah 2 action) | week 1: Theme kenyatta day to high profile candidate; week 2: xxx; week 3: xxx; week 8: Theme whole week patriotically 4 candidate; week 9: Theme jamhuri day to high profile candidate
| Rural Press | Cat | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview | Run features on regional papers with interview
| Rural Press | Dolphin | Articles to Cat on themed issues/message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message | Issue article to Cat on our issues to theme message
| Nationaly | Stork / Dolphin | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media
| FM stations | Bull | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support
Unpredictable
| Nationaly | Cheetah | week 1: RO's cabinet list leak-internet & Flyers; week 2: Radio/People/Kenya Times/Citizen (Stork)
| Nationaly | Stork | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media
| Cyberspace | Cheetah | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral | Internet / website spiral
| Telephone | Cheetah | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting
| Telephone | Giraffe | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending
| Nationaly | Stork / Dolphin | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media
| FM stations | Bull | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support
Unreliable
Party hopping | Telephone | Cheetah | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting | Sms message crafting
All luo MP’s are either his or Wife’s relatives except 1(Oburu, Midiwo, Sam Weya etc) | Telephone | Giraffe | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending | Sms message sending
E.A spectre 99% luos | Print | Dolphin | week 1: "Sold us to Americans" article-Sunday Nation
Luo Thrift Trading Company foundation of peasants earnings |  | Stork | xxx | "Wezi wa Kanu" Dolphin article on Citizen+E6 | "Why is RO suddenly so electable" | Article from Dolphin | Article from Dolphin | Article from Dolphin | Article from Dolphin | Article from Dolphin | Article from Dolphin | Article from Dolphin | Article from Dolphin | Article from Dolphin
| Print | Dolphin / Stork | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes | Letters to the Editors on these 4 themes
| Nationaly | Stork / Dolphin | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media
| FM stations | Bull | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support
Unstable
RO will be forced to reward ex 1982 soldiers out in cold leading to disgruntlement of serving soldiers who will revolt | Nationaly | Stork | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda | Kenya can become another Rwanda
Kenya can become another Rwanda | Nationaly | Stork | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media
| Nationaly | Stork / Dolphin | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media | Articles & letters to Editor on print media
| FM stations | Bull | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support | Generating talk shows & call-ins support
Increased Visibilty Project | COST
Commence radio testimonial advertisng |  | Giraffe
Commence Daily Newspaper Strips advertsing |  | Giraffe
Advertise on 200 Bus backs |  | Giraffe
Print & Distribute 200,000 Bumper stickers |  | Giraffe
Commision 12 Additional Bill boards in Nairobi/Msa |  | Giraffe
Erect 500 Street lights in Nairobi & Mombasa |  | Giraffe
Erect HIV/Aids Bill Board on Afya House |  | Giraffe
Commence advertising |  | Giraffe
Put 130 Countrywide Cheetah Bill Boards |  | Cheetar
Launch the Music campaign | 10000000 | Giraffe
Launch the Youth campaign | 50000000 | Giraffe
Controversy Stirring Project
NSE & anti business & free enterprise eg Jua kali
Re–introduction of price controls (ala Mugabe)
Majimbo
Tribal zoning / go back home
(create and "leak"Anti GEMA strategy through friendly media (Nation/People)
Election of Chiefs
All chiefs out of jobs after Dec
Crimes will escalate, chaos & disorder like after IPPG
Boma’s Draft key controversial issue
Welfare state will bank
Future Message “Hope Vs fear”
KM Project (on Hold)
Providing competition to RO in R. Valley & Western
Branding KM
Response-5 big issues Project
Unemployment
Poverty
Tribalism
Corruption
High cost of living
Branding our Candidate Project
Localisation of key issues
Message of future “Hope Vs fear”